## README
Last Update | 2018-11-02
Authors | Christopher Yee, Ruifeng Zhang, Huber Ochoa, Carl Bai
Email | cyee008@ucr.edu, hocho002@ucr.edu, rzhan016@.ucr.edu, carlbai66@gmail.com
Description | Our team of 4 is out to create a note taking app called SimpleNote. It shares many similarities to Google Keep, with a few extra features.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Data | As a new User, I have the option to register for an account. This will allow the app to be able to transfer my notes between devices. I also have the option to skip this, storing my notes locally on the device they are written on. | 5 | 1
7 | Notes | As a User, I want to be able to create and delete notes | 4 | 2
2 | Text editing | As a User, I am able to edit text of a newly created or old Note. | 1 | 3
3 | Images | As a User, I can insert images into my notes, just in case I need a visual representation in my notes. These images can be inserted from my phone’s Gallery or straight from the camera. | 6 | 4
4 | Drawing | As a user, I can draw over my notes and any inserted images. This will create the option of true-custom visuals for my notes. | 7 | 5 | May be split
5 | Labels | As a User, I can create my own Labels to organize my notes into. Labels are completely based on the User. | 3 | 6
6 | Lists | As a user, I can make interactive lists. These lists can have a title and text alongside a box that can be checked marked. | 6 | 7
8 | Customization | As a User, I can change the background color of each note to color code them. | 2 | 8
9 | Reminders | As a user, I can make notes as “reminders” by adding a time and date to a note. Doing so will let SimpleNote remind me at that time. I can set specific reminder times as well ways of reminder such as email or push notification. | 5 | 9
11 | Voice | As a User, I can add a voice recording to my notes and be able to play them back later. | 4 | 10 | Bonus feature
10 | Privacy | I can make certain notes password protected. This will ensure a level of privacy for notes with sensitive information. | 2 | 11 | Bonus feature
12 | Sharing | As a User, I can create a link to share specific notes with friends and family. | 4 | 12 | Bonus feature
| Total |  | 34

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Ruifeng Zhang | 4
2 | Christopher Yee | 6
3 | Ruifeng Zhang | ..

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Design login screen (Ruifeng Zhang, Huber Ochoa)
Task 2: Design user UI (Chris Yee, Carl Bai)
Task 3: Connect app to Firebase (Ruifeng Zhang, Huber Ochoa)
Task 4: User login (Ruifeng Zhang, Huber Ochoa)
Task 5: General UI (Carl, Chris)
Task 6: Adding and editing Text (Huber, Ruifeng)
Task 7: Text stylization (Carl)
Task 8: User image uploads (Huber)
Task 9: Displaying and formatting images (Huber)
Task 10: Drawing (Ruifeng, Huber, Chris)
Task 11: Organization of notes in UI (Chris, Ruifeng)
Task 12: Labels (Chris)
Task 13: Adding drawings to notes (Ruifeng, Huber,Chris)
Task 14: Storing notes online with firebase (Huber, Ruifeng)
Task 15: Synching notes between devices (Huber, Ruifeng)
Task 16: Set up android studio with github(all)
Task 17: Reminders (Carl, Chris)
Task 18: Sign Out(Ruifeng Zhang)
Task 19: Task List (Carl, Chris)

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 45 | 6 | 6 | 39 | 35
1 | 45 | 5 | 11 | 34 | 30.625
2 | 33 | 0 | 5 | 28 | 26.25
3 | 33 | 0 | 5 | 28 | 21.875
4 | 33 | 0 | 5 | 28 | 17.5
5 | 33 | 0 | 5 | 28 | 13.125
6 |  |  |  |  | 8.75
7 |  |  |  |  | 4.375
8 |  |  |  |  | 0